## Sheet1
Phase 1: Project setup |  | Time Estimation (Days)
Step 1: | Brainstorm feature backlog | 5
Step 2: | Verify features with client | 3
Step 3: | Finalize tools and technology | 2
Step 4: | Create storyboards and design diagrams. | 7
Step 5: | Get final OK from client | 2
Phase 2: Backend Development
Step 1: | Setup database/website backend (user accounts, login) | 10
Step 2: | Setup basic Javascript client | 10
Step 3: | Setup basic game-logic script (environment, plants, wind) | 10
Step 4: | Finalize custom AI scripting language | 5
Step 5: | Implement communication between JavaScript client and database | 3
Phase 3: Frontend Development
Step 1: | Create interface for uploading/sharing AI scripts. | 5
Step 2: | Upgrade game-logic script to allow AI avatars. | 20
Step 3: | Implement basic 2.5D graphics in client. | 20
Step 4: | Implement host pausing and rewinding of world. | 10
Step 5: | Implement spectator client interface. | 10
Step 6: | Implement random world generation. | 15
Step 7: | Implement user terrain editing. | 20
Phase 4: Finalization
Step 1: | Final large review of backlog and remaining time to prioritize. | 2
Step 2: | Upgrade client graphics and usability | 15
Step 3: | Upgrade website usability and style | 15
| Total Time: | 189